## Sheet1
S.No | Enhancement | Description | Status | Owner | Priority | Date Reported | Date Completed | Comments
1 | Smart Identification | Enable Fallback mechanism for object verification failures. Try out different approach at runtime to resolve the issue | Open |  | 4 | 2016-08-09
2 | Datadump path | Read it from framework.properties so we can change it for back up | Completed | Harsh | 1 | 2016-08-09 | 2016-08-30
3 | datadump file name | Use a unique id to differentiate between different dump files for the same test case | Open | Harsh | 2 | 2016-08-09
4 | Automatic Re run | For failures, set the PE_RERUN variable automatically to true | Open | Harsh | 2 | 2016-08-09
5 | externalize rerun parameter | for execution from Jenkins or command line, set up a mechanism to pass this variable to the framework | Open |  | 2 | 2016-08-09
6 | Rerun count | Set up a feature to specify the rerun count/in case of failure | Open | Harsh | 2 | 2016-08-09
7 | Selenium Grid implementation | set up multiple executors/threads on a remote driver and execute | Completed | Harsh | 1 | 2016-08-09 | 2016-09-16 | http://bsdqept-wc-02s.sys.comcast.net:4444/grid/console
8 | DataProvider | Check out the dataprovider annotation by testng to simulate load testing | In Progress | Kalyan | 2 | 2016-08-09 |  | Feasibility analysis to be done for load testing. Dataprovider and thread usage investigation is complete
9 | Database dump | Implement datadump using a database instead of a flat file | Open |  | 3 | 2016-08-09
10 | Git Process | Set up a branch for each release to enable versioning | Open |  | 2 | 2016-08-09
11 | Logging | Create a logging class which can be used in all other classes | Completed | Omkar | 1 | 2016-08-09
12 | Transaction Logging | Queue based performance monitoring with options to start and end a transaction | Completed | Omkar | 1 | 2016-08-09
13 | Method Headers for Java Doc | Add header description for methods for documentation | In Progress | Team | 2 | 2016-08-24
14 | Screenshots on failure | set a global variable that enables the screenshot level | Open | Harsh | 1 | 2016-08-09
15 | Ease of Running | Easy of running a single test 1. by developer/functional testers 2. Pause on error/continue …. 3. Step by Step execution, partial sequence of steps 4. Providing data locally … | Open |  | 3 | 2016-08-24
16 | OVT | Write Object Verification tests that check for any object property changes upfront to manage maintenance | In Progress | Kalyan | 1 | 2016-08-24
17 | Environment Validation | Health check script that tests if all the end points are configured correctly | Open | Sudhakar/Harsh | 1 | 2016-08-24
18 | API Testing/DB Testing | Any testing not on the UI layer | Open |  | 2 | 2016-08-24
19 | Admin | Slave Monitoring/Grid Monitoring | Open | Rijin/Team | 2 | 2016-08-24
20 | PhantomJS | Headless Test Automation | In Progress | Kalyan | 3 | 2016-08-24 |  | POC to integrate PhantomJS with Selenium/TestNG is complete
21 | Log Comparison | Compare Log files with previous runs | Open |  | 4 | 2016-08-24
22 | ALM Rest Integration | Update test status in ALM using ALM rest API | Completed | Harsh | 1 | 2016-08-29 | 2016-09-06
23 | Framework Context | Set up a framewor context object that will encapsulate all global data which will be passed around to test classes | Completed | Harsh | 1 | 2016-09-13 | 2016-09-16
24 | Multi-Dependency | Set up Multi Maven structure so to externalize reusable components for other projects to consume | Completed | Harsh/Omkar | 2 | 2016-09-19 | 2016-09-29
25 | DSL/Keyword based development | Set up a high level framework for functional testers to develop scripts with ease | Open | Harsh/Team? | 4 | 2016-09-30 |  | https://github.comcast.com/quality-driven-delivery/BSA_Selenium_Core