## Sheet1
S.No | Script Name | Package/Location | Review Comment | Assigned | Reviewer | Owner | Status | Date reported | Date fixed | Comments
1 | All | src/test/java/NewConnectTest.java | I see test methods with names ActivateService_EPL, EVPL etc. We should have a method for activateService and inside the page methods –we can have the logic to call it multiple times based upon the product type | Rijin/Kesavan/Jatin | Harsh | Team | Closed | 2016-09-02 | 2016-09-09
2 | All | src/test/java/NewConnectTest.java | NewConnectTest.java now has so many methods including coax flow – can we create a base class for coax/fiber separate? | Rijin/Kesavan/Jatin | Harsh | Team | Closed | 2016-09-02 | 2016-09-09
3 | All | src/test/java/NewConnectTest.java | The base scenario class has methods like -Ship_CPE_EVPL2 – I assume this is for the another flow after new connect – and this looks like a test case specific flow – these can go into the actual test class and inside it you can call super.methodname | Rijin/Kesavan/Jatin | Harsh | Team | Closed | 2016-09-02 | 2016-09-09
4 | All | src/test/java/NewConnectTest.java | Keep the common methods in base/scenario class like newconnecttest and others should be in specific test classes. | Rijin/Kesavan/Jatin | Harsh | Team | Closed | 2016-09-02 | 2016-09-09
5 | All | src/test/java/NewConnectTest.java | Same with CreateAddress1,2,3 – there should be just 1 method for createAddress | Rijin/Kesavan/Jatin | Harsh | Team | Closed | 2016-09-02 | 2016-09-09
6 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | I observe that we have not implemented the isValidPage method (abstract method from Page.java) in all our page classes. We should implement this for every page to look for an element on that page to identify that it is in the same page @Override protected boolean isValidPage() { return false; } | Rijin/Kesavan/Jatin | Harsh |  | Open | 2016-09-27
7 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | We should use the id/class locator instead of xpath when we are referencing the id/class property in the xpath string. For e.g. in the below webelements, we should change the findby attribute to id instead of xpath @FindBy(xpath = "//*[@id='addcontact-toolEl']") | Rijin/Kesavan/Jatin | Harsh | Kesavan | Closed | 2016-09-27 | 2016-10-04
8 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | I still see that there are few link or button clicks that are not handled with page.java metho (Iclick) for.e.g. - in AccountTabPageCM.java. Line num 156, line 189 | Rijin/Kesavan/Jatin | Harsh |  | Open | 2016-09-30
9 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | CSO Page classes have common methods that should be moved into Page.java or CenturyPage.java - clickBackButton, clickSaveButton, clickContinueButton getResourceComponentID ClickCompleteButton | Rijin/Kesavan/Jatin | Harsh |  | Open | 2016-10-03
10 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | Many classes still don’t use the updated iClick method – for e.g. ManageTab.java#createLabel | Rijin/Kesavan/Jatin | Harsh |  | Open | 2016-10-03
11 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | Exceptions – wherever we catch exceptions, please write the exception details into logger using log.info and return the status with mstatus | Rijin/Kesavan/Jatin | Harsh | Kesavan | Open | 2016-10-03 | 2016-10-04
12 | All | src/test/java/com/comcast/century/cm/pages src/test/java/com/comcast/century/cm/pages | Kalyan is working on OR per page – but we will also need a common OR file also for referencing to common objects in all page files – like worklist methods, continue button, save, frames etc | Rijin/Kesavan/Jatin/Kalyan | Harsh |  | Open | 2016-10-03